|  | Programme Programm (PBB) | Sub- (PBB) | 2024 ANNUAL ACTION PLAN Broad Activities | Location | Time Frame (2024) |  |  |  | Cost (GHc) |  |  |  |  |  | Programme status |  |  |  | Implementing Agencies |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GOG | IGF |  | Others |  | New |  | On-going |  | Lead |  | Collaboration |
|  | ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | FINANCIAL MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Revenue mobilization and expenditure management improvement | Revenue mobilization | Strengthen Municipal Revenue Taskforce | Municipal Wide |  |  |  |  |  | 2,000.00 |  | 5,000.00 |  |  |  | √ |  | Finance Dept. |  | MA Revenue Collectors Rate payers Budget Office Dept. of Spatial Planning |
|  |  |  | Develop and implement revenue improvement plan | Municipal Wide |  |  |  |  |  | 5,000.00 |  | 20,000.00 |  |  |  | √ |  | Finance Dept. |  | MA Revenue Collectors Rate payers Budget Office Dept. of Spatial Planning |
|  |  |  | Update data on all ratable properties in the Municipal, annually | Municipal wide |  |  |  |  |  | 10,000.00 |  | 30,500.00 |  |  |  | √ |  | Finance Dept. |  | MA Revenue Collectors Rate payers Budget Office Dept. of Spatial Planning Internal Audit Unit |
|  |  | Training on Revenue Improvement Strategy /Revenue Collection | To equip officers with the necessary techniques in revenue mobilization | Nkawie |  |  |  |  |  | 5,000.00 |  | 20,000.00 |  |  |  | √ |  | Finance Dept. |  | MA/Revenue Collectors/Rate payers /Budget Office/Dept. of Spatial Planning /CSOs/IAU |
|  | BUSINESS ADVISORY CENTRE (BAC) ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Register 100 youth (16-35) to establish their businesses through Youth entrepreneurship programme(Youth Start) | Municipal wide |  |  |  |  |  |  |  | 5,000.00 |  | √ |  |  |  | BAC |  | NBSSI, Mastercard Foundation |
|  |  |  | Organize Business counseling for 200 BAC clients | Municipal wide |  |  |  |  |  | 4,000.00 |  |  |  |  |  | √ |  | BAC |  | MA/REP/NBSSI |
|  |  |  | Sensitize 100 entrepreneurs to formalize their businesses at RGDs,FDA, GSA. | Municipal wide |  |  |  |  |  |  |  | 2,000.00 |  |  |  | √ |  | BAC |  | CLIENTS |
|  | Tourism Developmet | Tourism Infrastructual Deevelopment | Dredging of 4 No. fish pond | Nkawie |  |  |  |  |  |  |  | 22,000.00 |  |  |  |  |  | MA |  | Tourism and Culture Dept |
|  | AGRICULTURAL ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Agriculture productivity enhancement | increase crop production | Nursery establishment for 30,000 coconut and oil palm Seedlings for farmers | Municipal wide |  |  |  |  |  |  |  | 90,000.00 |  |  |  | √ |  | Agric. Dept. |  | MA |
|  |  | Introduce climate Smart agriculture to farmers | Embark on sensitization and education on climate change | Municipal wide |  |  |  |  |  |  |  | 10,000.00 |  |  |  | √ |  | Agric. Dept. |  | NADMO/MAG/FIRE SERVICE |
|  |  |  | Liaise with fire service to educate communities on the control of bushfires |  |  |  |  |  | 3,100.00 |  |  | 5,400.00 |  |  |  | √ |  | Agric. Dept. |  | NADMO/MAG/FIRE SERVICE |
|  |  | Livestock Development | Training on Anti-rabies, feed preparation for birds, disease surveillance, animal housing and management | Municipal wide |  |  |  |  |  |  |  | 5,730.00 |  |  |  | √ |  | Agric. Dept. |  | MAG/NGO |
|  |  | Postharvest management | Training of staff in postharvest management, agricultural value chain, rice extensions, FBO formation, etc. | Municipal wide |  |  |  |  |  |  |  | 3,000.00 |  |  |  | √ |  | Agric. Dept. |  | MAG/MA/NGO |
|  |  | Extension delivery | Conduct staff and home visits and monitor Planting for Food and Job fields | Municipal wide |  |  |  |  |  |  |  | 19,800.00 |  |  |  | √ |  | Agric. Dept. |  | MA/MAG/NGO/JICA |
|  | Agric-Business Development | Women empowerment | Train 200 lactating women farmers on formulation of fortified food for infants/babies under 5yrs | Municipal wide |  |  |  |  |  |  |  | 3,000.00 |  | √ |  |  |  | Agric. Dept. |  | MAG/MA/NGO/ |
|  |  |  | Train 100 women on liquid soap and shower gel preparation | Municipal wide |  |  |  |  |  |  |  | 7,500.00 |  |  |  | √ |  | Agric. Dept. |  | MA/MAG/NGO/JICA/HEALTH, BAC |
|  |  |  | Monitoring of agro-inputs shops | Municipal wide |  |  |  |  |  |  |  | 1,300.00 |  |  |  | √ |  | Agric. Dept. |  | MA |
|  | Technology dissemination |  | Organize RELC activities |  |  |  |  |  |  |  |  | 3,000.00 |  |  |  | √ |  | Agric. Dept. |  | MA |
|  | Sector management enhancement | Monitoring and evaluation | Conduct MDOs supervision and monitor activities of extension staff | Municipal wide |  |  |  |  |  |  |  | 14,400.00 |  |  |  | √ |  | Agric. Dept. |  | MA |
|  |  |  | Conduct monitoring and evaluation of all Agric projects by MMA, MCD, and MCE | Municipal wide |  |  |  |  |  |  |  | 4,000.00 |  |  |  | √ |  | Agric. Dept. |  | MA |
|  |  |  | Conduct data collection of crops, livestock, market, tree crops, processing facilities, agro inputs outlets, etc. | Municipal wide |  |  |  |  |  |  |  | 2,600.00 |  |  |  | √ |  | Agric. Dept. |  | MA |
|  |  |  | Conduct baseline and yield studies on cereals, roots and tubers, legumes, plantain and vegetables. | Municipal Wide |  |  |  |  |  |  |  | 9,342.00 |  |  |  | √ |  | Agric Dept. |  | Statistical Service |
|  |  |  | Training and development education training on modernization of Agriculture (TEDMAG) | Nkawie |  |  |  |  |  |  |  | 6,519.00 |  |  |  | √ |  | Agric Dept. |  | M/A |
|  |  |  | Establish rice extension training programme for staff and rice farmers. | Municipal Wide |  |  |  |  | 6,750.00 |  |  | 6,000.00 |  |  |  | √ |  | Agric Dept. |  | M/A |
|  |  |  | Participate in review meeting and national workshops | Municipal Wide |  |  |  |  | 1,129.00 |  |  | 4,071.00 |  |  |  | √ |  | Agric Dept. |  | M/A/Health Directorate. |
|  |  |  | Establish maize farm demonstrations on GAPS | Municipal Wide |  |  |  |  |  |  |  | 5,850.00 |  |  |  | √ |  | Agric Dept. |  | M/A |
|  |  |  | Sensitization of pests and diseases surveillance e.g (FAW). | Municipal Wide |  |  |  |  |  |  |  | 300.00 |  |  |  | √ |  | Agric Dept. |  | M/A |
|  |  |  | Training of technical staff on pest and diseases identification in vegetable production. | Municipal Wide |  |  |  |  |  |  |  | 2,060.00 |  |  |  | √ |  | Agric Dept. |  | M/A |
|  |  |  | Participate in regional JCR meetings | Municipal Wide |  |  |  |  | 1,500.00 |  |  | 2,328.00 |  |  |  | √ |  | Agric Dept. |  | M/A |
|  |  |  | Conduct farmers forum and create awareness on PFJ and child labour | Municipal wide |  |  |  |  |  |  |  | 1,750.00 |  |  |  | √ |  | Agric Dept. |  | M/A |
|  |  |  | Farmers Day celebration |  |  |  |  |  | 1,000.00 |  |  | 80,000.00 |  |  |  | √ |  | Agric Dept. |  | M/A |
|  | TRADE AND INDUSTRY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Economic Development | Trade and Industry | Completion of 1 storey 26 lockable stores with washrooms | Toase |  |  |  |  |  |  |  | 1,100,000.00 |  |  |  | √ |  | Works Dept. |  | Central Admin |
|  | SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EDUCATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Educational environment improvement | School management system | Supervision and monitoring of attendance and performance of Teachers and pupils in public schools. | Municipal wide |  |  |  |  | 5,640.00 |  |  |  |  |  |  | √ |  | Municipal Directorate of Education |  | Municipal Assembly, NGOs, GES, MoE |
|  |  |  | Organize INSET on Early Childhood Education | Selected Schools |  |  |  |  | 2,750.00 |  |  |  |  |  |  | √ |  | Municipal Directorate of Education |  | Municipal Assembly, NGOs, GES, MoE, GEFUND |
|  |  | My First Day at School Programme | To welcome and encourage KG 1 and Primary 1 Learners to attend school regularly |  |  |  |  |  |  | 6,000.00 |  |  |  |  |  | √ |  | Municipal Directorate of Education |  | Municipal Assembly, NGOs, GES, MoE, GEFUND |
|  |  | Performance enhancement | Conduct Mock Exams twice for BECE and WASSCE candidates | Municipal wide |  |  |  |  |  |  |  | 20,000.00 |  |  |  | √ |  | Municipal Directorate of Education |  | Municipal Assembly, NGOs, GES, MoE, GEFUND |
|  |  |  | Manufacture 100 no teachers table, 100 no teachers chair and 400 no dual desk | Municipal wide |  |  |  |  |  |  |  | 400,000.00 |  |  |  | √ |  | Municipal Directorate of Education |  | Municipal Assembly, NGOs, GES, MoE, GEFUND |
|  |  |  | Provide financial support for 100 needy but brilliant students | Municipal wide |  |  |  |  |  |  |  | 25,000.00 |  |  |  | √ |  | MA |  | NGOs, GES, MoE, GEFUND |
|  |  | Infrastructural enhancement | Completion of 3No. 6-Unit Classroom Block with ancillary facilities with landscaping | Abuakwa Boaso |  |  |  |  |  |  |  | 1,600,000.00 |  | √ |  |  |  | MA |  | Municipal Assembly, NGOs, GES, MoE, GETFUND |
|  | HEALTH CARE SERVICE DEVELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Infant and maternal health improvement | Infant health improvement | Conduct routine immunization as part of the Expanded Programme (EPI) to protect children under five | Municipal wide |  |  |  |  |  |  |  |  | 15,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  |  |  | Organize health education on exclusive breastfeeding using behavior change communication strategy at public and social gatherings | Municipal wide |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  |  |  | Organize Child Health Promotion Weeks | Municipal wide |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  |  |  | Identification and registration of children, OVCs/PLWHAs and the vulnerable with NHIS | Municipal wide |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  |  | Maternal health improvement | Conduct routine immunization as part of the Expanded Programme (EPI) to protect pregnant women. | Municipal wide |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  | Health care delivery enhancement | Health Personnel management | Carry out monitoring and supervision on family planning | Municipal Wide |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  |  |  | Support to Roll Back Malaria programme (0.5%) | Municipal Wide |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  | Reducing the incidence of HIV, other STIs and improve the health of victims |  | Support to Municipal response initiative (0.5%) on HIV/AIDS | Municipal wide |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  |  |  | Organize Know Your Status campaign on HIV/AIDS | Municipal Wide |  |  |  |  |  |  | 1,000.00 |  | 5,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  |  |  | Construction of 1No. Health centre | Besease |  |  |  |  |  |  |  |  | 600,000.00 |  | √ |  |  |  | GHS | MoH/MA |
|  |  |  | Purchase of medical equipment for health centres | Health Centres |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  | √ |  | GHS | MoH/MA |
|  |  |  | Mass registration of birth and death in selected commubnities | Abuakwa Mim Nkawie Sepaase |  |  |  |  |  |  | 3,000.00 |  | 5,000.00 |  | √ |  |  |  | Birth and Death Registry | GHS ANMA |
|  |  |  | Public education on the essence of birth and death registration | Municipal wide |  |  |  |  |  |  |  |  | 7,000.00 |  | √ |  |  |  | Birth and Death Registry | GHS ANMA |
|  |  |  | Preparation and submission of data to GSS | Nkawie |  |  |  |  | 1,500.00 |  |  |  |  |  | √ |  |  |  | Birth and Death Registry | GHS ANMA |
|  | SOCIAL PROTECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Support to Child Labor Free Zone Program | Support Child Labor Free Zone Program in 20 communities | 20 selected communities |  |  |  |  |  | 2,000.00 |  | 10,000.00 |  |  |  |  |  | SWCD |  | MA/NGOs |
|  |  |  | Management of reported child protection cases |  |  |  |  |  | 1,000.00 |  |  |  |  |  |  |  |  | SWCD |  | NGO / CSOs |
|  |  |  | Commemoration and celebration of World’s Day against child labor |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  | SWCD |  | MA/COCOABOD / MA/NGOs / AGRIC DEPT/ cocoabod |
|  |  |  | Support to indigents for registration and renewal of NHIS | Municipal wide |  |  |  |  |  |  |  | 3,000.00 |  |  |  |  |  | SWCD |  | GHS / NHIA |
|  |  | Monitoring of Day care centers. Residential home and hospital/health centers in the Municipal | To ensure that institutions are providing quality care for children and work with them to resolving challenges relating to their service | Municipal wide |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  |  | SWCD |  |  |
|  |  | Public education | Public education on child protection issues, teenage pregnancy, child labor, etc. | Municipal wide |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  |  | SWCD |  | NCCE / CSO / NGO |
|  |  |  | Public education on domestic violence and gender based violence | Municipal wide |  |  |  |  | 2,000.00 |  |  |  |  |  |  |  |  | SWCD |  | GPS / DOVVSU |
|  |  | Conflict resolution and administration of justice | Resolution of domestic violence and gender based violence cases | Municipal wide |  |  |  |  | 1,000.00 |  |  |  |  |  |  |  |  | SWCD |  | DOVVSU / GPS |
|  |  |  | Dissemination of helpline (center of hope) in the Municipal | Municipal wide |  |  |  |  | 2,000.00 |  |  |  |  |  |  |  |  | SWCD |  | ISD / NCCE |
|  |  | Women empowerment | Engagement with women’s groups/associations in the Municipal | Municipal wide |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  | SWCD |  | AGRIC DEPT / BAC /NGOS / CSOS |
|  | Employable skills development and job creation for the vulnerable | Skills and training | Organize 2-Day training workshop for 20 PWDs on how to start small scale business and its sustainability | Municipal wide |  |  |  |  |  |  |  | 7,000.00 |  |  |  | √ |  | SWCD |  | MA/REP/ BAC |
|  |  |  | Register and organize training workshops for 50 vulnerable and excluded in the Municipal on alternative livelihood | Municipal wide |  |  |  |  |  |  |  | 6,500.00 |  |  |  | √ |  | SWCD |  | MA/REP/ BAC |
|  |  | Job creation | Supply technical aid and equipments in forms of Sewing Machines, Motor Machines, Locking Machine, Grinding Machine, Dryer and Hand Dryer, Fridges to support PWDs apprenticeship. | Municipal wide |  |  |  |  |  |  |  | 13,000.00 |  |  |  | √ |  | SWCD |  | MA/REP/BAC |
|  | WATER AND SANITATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | WATER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Potable water supply improvement | Water facility expansion | Drilling and mechanization of 3No. Borehole | Dadiese market, Abuakwa market and Abuakwa SHS |  |  |  |  |  |  |  | 135,000.00 |  |  |  | √ |  | ENV’TAL, WORKS DEPT. |  | MA/NGOs/MEHU |
|  |  | Drilling and Mechanization of 1No. with 2HP submersible pump with Reinforced concrete stand |  | Abuakwa Boaso |  |  |  |  |  | 5,000.00 |  | 150,000.00 |  |  |  |  |  | ENV’TAL, WORKS DEPT |  | Central Admi |
|  | SANITATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Sanitation improvement |  | Organizing quaterly clean up exercise in each area council | Municipal Wide |  |  |  |  |  |  |  | 25,000.00 |  |  |  | √ |  | ENV’TAL HEALTH/ZOOMLION |  | MA/WORKS DEPT. |
|  |  |  | Periodic pushing and leveling of Final Disposal site | Nkawie, |  |  |  |  |  |  |  | 150,000.00 |  |  |  | √ |  | ENV’TAL, ZOOMLION |  | MA/ WORKS DEPT. |
|  |  |  | Disinfection of public spaces | Municipal Wide |  |  |  |  |  |  |  | 80,000.00 |  |  |  | √ |  | ENV’TAL, ZOOMLION |  | MA/ WORKS DEPT. |
|  |  |  | Conduct Premises inspection in Residential houses and schools | Municipal wide |  |  |  |  |  | 4,600.00 |  |  |  |  |  | √ |  | DWST |  | MA/MEHU |
|  |  |  | Procure Sanitary Equipment | Municipal wide |  |  |  |  |  | 12,000.00 |  |  |  |  |  | √ |  | DWST |  | MA/MEHU |
|  |  |  | Clearing and maintaining of open public areas | Municipal wide |  |  |  |  |  | 3,000.00 |  |  |  |  |  | √ |  | DWST |  | MA/NGOs/MEHU |
|  |  |  | Screening of food vendors | Municipal wide |  |  |  |  |  | 4,300.00 |  |  |  |  |  | √ |  | DWST |  | MA/MEHU |
|  | ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UTILITY SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Utility services expansion |  | Reshaping 45km of road, spot improvement and landscaping (DRIP) | DKC, Manhia, Apemhaase, Boaso, Cainan, Nkawie panin, Mfensi, Sewua Nkontonmire |  |  |  |  |  | 50,0000 |  | 500,000.00 |  |  |  | √ |  | Feeder Roads |  | Works Dept. |
|  |  |  | Desilting of river bodies | Apemhase Abuakwa DKC |  |  |  |  |  |  |  | 1,250,000.00 |  |  |  | √ |  | Works Dept. |  | MA |
|  |  |  | Training of transport operators in road traffic management and transport policies (road safety) | Selected communities |  |  |  |  |  |  |  | 2,500,000.00 |  |  |  | √ |  | Feeder Roads GPRTU |  | Works Dept. |
|  |  |  | Procure and supply street bulbs, maintenance of street lights | Municipal wide |  |  |  |  |  | 15,000.00 |  | 50,000.00 |  |  |  | √ |  | Procurement |  | MA/Works Dept. |
|  | Disaster prevention and management |  | Organize 2No. community forums to sensitize communities on the issues of climate change | Municipal wide |  |  |  |  |  |  |  | 13,000.00 |  |  |  | √ |  | NADMO |  | MA |
|  |  |  | Bush and domestic fire education. | Municipal Wide |  |  |  |  |  | 6,000.00 |  |  |  |  |  | √ |  | NADMO/FIRE SERVICE |  | MA/DVGs |
|  |  |  | Tree planting exercise | Municipal Wide |  |  |  |  |  | 5,000.00 |  | 20,000.00 |  |  |  | √ |  | NADMO/FORESTRY |  | DVGs, ASSEMBLY MEMBERS |
|  |  |  | Renovation of Lorry terminal | Nkawie |  |  |  |  | 20,000.00 |  |  | 140,000.00 |  |  |  |  |  |  |  | Central Admin, Works Dept, Dev’t Planning |
|  |  |  | Train Disaster Volunteer Groups on bushfire control | Municipal wide |  |  |  |  |  | 3,500.00 |  | 4,000.00 |  |  |  | √ |  | NADMO |  | MA |
|  | SPATIAL PLANNING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Prepare local plans for 2 communities (Base Maps) | Toase Abuakwa |  |  |  |  |  | 5,000.00 |  | 60,000.00 |  |  |  |  |  | PPD |  | Central Admin, Works Dept, Dev’t Planning |
|  |  |  | Conduct monthly site inspections &development control | Municipal Wide |  |  |  |  |  | 3,000.00 |  | 20,000.00 |  |  |  |  |  | PPD |  | Central Admin, Works Dept, Dev’tPlanning |
|  |  |  | Support street naming and property addressing | Municipal widee |  |  |  |  |  | 10,000 |  | 50,0000 |  |  |  |  |  | PPD |  | Central Admin, Works Dept, Dev’tPlanning |
| GOVERNANCE, CORRUTPION AND ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Organize Quarterly Statutory Sub-Committee Meetings | Nkawie |  |  |  |  |  | 6,500.00 |  | 26,000.00 |  |  |  | √ |  | MA |  | Assembly Members |
|  |  |  | Organize Quarterly and Annual AAP Review Meetings | Nkawie |  |  |  |  |  | 4,000.00 |  | 8,000.00 |  |  |  | √ |  | Planning Unit |  | MA HODs |
|  |  |  | Town Hall meetings |  |  |  |  |  | 80,000.00 |  |  | 120,000.00 |  |  |  |  |  | Central Admin |  | Central Admin/MA |
|  |  |  | Conduct Participatory Monitoring of programmes and projects | Nkawie |  |  |  |  | 10,000.00 |  |  | 170,000.00 |  |  |  | √ |  | MPCU |  | MA, Project Beneficiaries Assembly Members Municipal Monitoring Team Service Providers TAs |
|  |  |  | MCE engagement | Municipal wide |  |  |  |  | 100,000.00 |  |  | 150,000.00 |  |  |  |  |  | Central Admin |  | Central Admi/MA |
|  | To ensure efficiency in work delivery | To provide support to the sub-structures | Support to 3 Sub Municipal Structures and community initiated projects | Nkawie Afari Abuakwa |  |  |  |  |  | 20,000.00 |  | 300,000.00 |  |  |  | √ |  | Central Admin |  | Area Council Executives |
|  |  | To ensure departmental activities are carried out effectively. | Support to other departmental Activities | Nkawie |  |  |  |  |  | 2,000.00 |  | 24,000.00 |  |  |  | √ |  | Central Admin |  | Heads of Departments |
|  |  | To improve the capacity of staff by organizing trainings | Organize Capacity Building Training for MA Staff | Nkawie |  |  |  |  | 10,000.00 | 2,000.00 |  | 15,000.00 |  |  |  | √ |  | Central Admin |  | Human Resource Manager |
|  |  | To ensure all public celebrations are observed in orderly manner | Support the celebration of national programmes (6th March, AU Day etc.) | Nkawie |  |  |  |  |  | 2,000.00 |  | 35,000.00 |  |  |  | √ |  | Central Admin |  | Stakeholders |
|  |  | To Improve the quality of work by providing the necessary logistics to each department when the need arise | Procure Office logistics such computers, laptops, printers, Stationery and Equipment, tables and chairs | Nkawie |  |  |  |  | 2,000.00 | 10,000.00 |  | 60,000.00 |  |  |  | √ |  | Central Admin |  | Procurement Unit |
|  |  | To ensure hon. Assembly members are well motivated during meetings | Sitting Allowances and end of year incentive packages to Hon. Assembly Members | Nkawie |  |  |  |  | 180,000.00 |  |  | 80,000.00 |  |  |  | √ |  | Central Admin |  | Finance Dept. |
|  |  | Ensure the Municipal Assembly official vehicles are functioning | Maintenance of Municipal Assembly Official Vehicles | Nkawie |  |  |  |  | 4,000.00 | 25,000.00 |  | 35,000.00 |  |  |  | √ |  | Central Admin |  | Transport Manager |
|  |  | To provide safe and comfortable working environment | Maintenance of Municipal Assembly Office buildings | Nkawie |  |  |  |  |  | 1,000.00 |  | 200,000.00 |  |  |  | √ |  | Central Admin |  | Works Dept. |
|  |  |  | Payment of utility bills | Nkawie |  |  |  |  |  | 1,000.00 |  | 70,000.00 |  |  |  | √ |  | Central Admin |  | Utility Service Providers |
|  |  |  | Beautification and Landscaping of Assembly premises | Nkawie |  |  |  |  |  |  |  | 2,000,000.00 |  |  |  | √ |  | Central Admin |  | Works Dept. |
|  |  | Support security service providers | Support to security services | Nkawie |  |  |  |  | 1,000.00 | 500.00 |  | 10,000.00 |  |  |  | √ |  | Central Admin |  | Security Service Provider |
|  |  |  | Plan/Budget preparation | Nkawie |  |  |  |  |  |  |  | 30,000.00 |  |  |  | √ |  | Central Admin |  | Budget Unit |
|  |  |  | Completion of 1No. Storey 6-Unit Flat | Toase |  |  |  |  |  | 30,000.00 |  | 225,000.00 |  |  |  | √ |  | Central Admin |  | Works Dept. |
|  |  |  | Construction of police post | Koben |  |  |  |  |  | 25,000.00 |  | 100,000.00 |  | √ |  |  |  | Central Admin |  | Works Dept. |